## Table 1
Y100 Blandford Estate Budget Estimates 04/10/2024
| Presentation 1 |  | Presentation 2 |  | Current Cost Plan
| Budget Estimate |  | Budget Estimate |  | Budget Estimate
Dates | 2023-03-09 |  | 2023-03-14 |  | 2024-10-04
Farnham House
Works (Excluding Block Lighting) | £ | 288618 | £ | 184500 | £ | 80232
Block Lighting | £ | 29000 | £ | 56000 | £ | 14392
Design | £ | 3393 | £ | 4690 | £ | 986
Prelims | £ | - | £ | 82367 | £ | 98301
Contractors OHP | £ | - | £ | 25981 | £ | 12959
Inflation | £ | 57000 | £ | 72150 | £ | 0
Sub total | £ | 378011 | £ | 425688 | £ | 206870
Lascelles House
Works (Excluding Block Lighting) | £ | 286402 | £ | 180318 | £ | 79218
Block Lighting | £ | 29000 | £ | 56000 | £ | 14392
Design | £ | 2955 | £ | 4647 | £ | 1122
Prelims | £ | - | £ | 82367 | £ | 90814
Contractors OHP | £ | - | £ | 25792 | £ | 12250
Inflation | £ | 56000 | £ | 73472 | £ | 0
Sub total | £ | 374357 | £ | 422596 | £ | 197796
Mordern House
Works (Excluding Block Lighting) | £ | 282050 | £ | 181409 | £ | 87878
Block Lighting | £ | 29000 | £ | 56000 | £ | 14392
Design | £ | 2981 | £ | 4668 | £ | 1022
Prelims | £ | - | £ | 82367 | £ | 100437
Contractors OHP | £ | - | £ | 25886 | £ | 13232
Inflation | £ | 57000 | £ | 73811 | £ | 0
Sub total | £ | 371031 | £ | 424141 | £ | 216961
Wimbourne House
Works (Excluding Block Lighting) | £ | 280412 | £ | 180814 | £ | 87028
Block Lighting | £ | 29000 | £ | 56000 | £ | 14392
Design | £ | 2963 | £ | 4657 | £ | 1022
Prelims | £ | - | £ | 82367 | £ | 99602
Contractors OHP | £ | - | £ | 25835 | £ | 12131
Inflation | £ | 57000 | £ | 73626 | £ | 0
Sub total | £ | 369375 | £ | 423299 | £ | 214175
Estate Works
Works | £ | 146039 | £ | 86950 | £ | 59545
Design | £ | 1832 | £ | 1696 | £ | 586
Prelims | £ | - | £ | 82367 | £ | 79876
Contractors OHP | £ | - | £ | 12811 | £ | 6876
Inflation | £ | 25700 | £ | 26085 | £ | 385
Sub total | £ | 173571 | £ | 209909 | £ | 147268
Tenanted Works
Works | £ | 122750 | £ | 71750 | £ | 0
Design | £ | 1696 | £ | 2798 | £ | 0
Prelims | £ | - | £ | 82367 | £ | 0
Contractors OHP | £ | - | £ | 11599 | £ | 0
Inflation | £ | 21600 | £ | 21525 | £ | 0
Sub total | £ | 146046 | £ | 190039 | £ | 0
Contingency @ 10% | £ | - | £ | 209567 | £ | 110517
WCC Costs @ 9% | £ | - | £ | 207472 | £ | 122108
Total Costs | £ | 1812391 | £ | 2512711 | £ | 1215695
Notes:
1. Since Presentation 2, some of the design and preliminary costs have been found to be inaccurate. These will be corrected during the current review phase before being passed to the contractor for design development and pricing.
2) OHP = Overhead and Profit
3) WCC = Westminster City Council
4) Tennated Works have been included within the individual blocks