## Summary & Marking Guidance
Huguenot House
Evaluation Scoring Summary
Criteria:
Each criteria/ sub criteria (measurable outcome) have equal weighting
Each measurable outcome to be assessed by relevant Consultant as a R/Y/G
Overall rating for each objective determined by the highest no. of either R/Y/G sub-criteria ratings
Westminster City Council Criteria | 2018 option | 2020 option | 2018 option | 2010 option | 2018 option | 2020 option | 2018 option | 2020 option | 2018 option | 2020 option | 2018 option | 2020 option | 2020 option
| Convert offices to homes | Convert offices to homes | Retain and Extend (2004 Podium Scheme) | Retain and Extend (2004 Podium Scheme) | Maintenance | Maintenance | Refurbishment | Refurbishment | Sale of the building | Sale of the building | Redevelopment (4a) | Redevelopment (4a) | Redevelopment (New)
Create new, local employment opportunities
Improve the quality of the built environment
Enable the development of a smart city
Preserve and enhance local communities
Provide a mix of homes across all tenures including affordable provision
Deliver a carbon efficient strategy that is environmentally sustainable
Develop a financially viable option which considers the duty of the Council to deliver value for money
Facilitate improvement of the quality of the public realm and reduce anti-social behaviour
Minimise disruption for existing residents as much as possible
Ensure that homes meet modern standards
Modern leisure, commercial facilities and homes
OUTCOME

## Measurable Outcomes
Measurable Outcomes *
WCC Criteria | Measurable Outcome | Objective Met | Objective Partially Met | Objective Not Met | Brief Commentary and Justification | 2018 option |  | 2020 option |  | 2018 option |  | 2020 option |  | 2018 option |  | 2020 option |  | 2018 option |  | 2020 option |  | 2018 option |  | 2020 option |  | 2018 option |  | 2020 option |  | 2020 option
[6 empty] | Convert offices to homes |  | Convert offices to homes |  | Retain and Extend (2004 Podium Scheme) |  | Retain and Extend (2004 Podium Scheme) |  | Maintenance |  | Maintenance |  | Refurbishment |  | Refurbishment |  | Sale of the building |  | Sale of the building |  | Redevelopment (4a) |  | Redevelopment (4a) |  | Redevelopment (New)
[6 empty] | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment | Assessment of Measurable Outcomes | Overall Assessment
Create new, local employment opportunities | Number of apprenticeships created in construction process. – confirmed measure will be contract value and associated number of required apprenticeships. | Estimated maximum number of construction apprenticeships to be provided in line with Planning requirements - proportionate to contract value. | Potential but not guaranteed opportunities for apprenticeships | No opportunities for apprenticeships |  | 0.8% |  | 0.8% |  | 2.9% |  | 2.9% |  | 0.4% |  | 0.4% |  | 0.6% |  | 0.6% |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 3.5% |  | 3.5% |  | 3%
| Number of local jobs created in construction process. Measure significant? (Limited) | More than 3% of local construction jobs created as a % of residents with construction jobs living in CoW | Between 1% and 3% of local construction jobs created as a % of residents with construction jobs living in CoW | Less than 1% of local construction jobs created as a % of residents with construction jobs living in CoW |  | 0.1% |  | 0.1% |  | 1.4% |  | 1.4% |  | 0% |  | 0% |  | 0% |  | 0% |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 2.4% |  | 2.4% |  | 2.4%
| Number of local jobs created in the operational phase | More than 0.3% of local operational jobs created as a % of residents with jobs in relevant industries living in CoW | Between 0.1% and 0.3% of local operational jobs created as a % of residents with jobs in relevant industries living in CoW | Less than 0.1% of local operational jobs created as a % of residents with jobs in relevant industries living in CoW |  | 0% |  | 0% |  | 0.05% |  | 0.05% |  | 0% |  | 0% |  | 0% |  | 0% |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 0.07% |  | 0.07% |  | 0.07%
| Employment creation numbers associated with each proposed use compared against the baseline (current position) define limited? | More than 0.3% of gross additional jobs as a proportion of the ward's employment | Between 0.1% and 0.3% of gross additional jobs as a proportion of the ward's employment | Less than 0.1% of gross additional jobs as a proportion of the ward's employment |  | 0% |  | 0% |  | 0.12% |  | 0.12% |  | 0% |  | 0% |  | 0% |  | 0% |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 0.17 |  | 0.17 |  | 0.17
| Residential design to enable home working. | Residential floor layouts maximised and incorporate sufficient space for a separate working area. | Working area incorporated into the main design of the unit. Limited space included for separate area. | Residential layouts do not enable a separate area for working. |  | No improvement |  | Layouts of new residential floors layouts could be reviewed to allow WFH - may lead to area/ unit no. changes |  | Unit layouts increased in area and mix so could be reviewed to accommodate WFH |  | Unit layouts increased in area and mix so could be reviewed to accommodate WFH |  | No improvement |  | Layouts of new residential floors layouts could be reviewed to allow WFH - may lead to area/ unit no. changes |  | No change in unit layouts to accommodate WFH |  | No change in unit layouts to accommodate WFH |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Unit areas to current area allowances so WFH area might be provided |  | Unit areas to current area allowances so WFH area might be provided |  | Unit layouts to current space standards - desk space to be planned.
Improve the quality of the built environment | Benchmark quality of the proposed option against the existing and proposed buildings within the local vicinity | Strong positive improvement to the quality/character of local built environment | Minor positive improvement to quality/character of local built environment | No improvement to the quality/character of local built environment, or negative impact. No perceived improvement |  | No improvement |  | Replace façade, roof and windows (as in Refurbishment option) |  | Redeveloped podium building with high quality architecture will enhance quality/character of local built environment (subject to design) |  | Redeveloped podium building with high quality architecture will enhance quality/character of local built environment (subject to design) |  | No material change to existing appearance |  | No material change to existing appearance |  | Replace façade , roof and windows |  | Replace façade , roof and windows |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Redeveloped building with high-quality architecture will enhance the local built environment (subject to design) |  | Redeveloped building with high-quality architecture will enhance the local built environment (subject to design) |  | Redeveloped building with high quality architecture will enhance quality/character of local built environment (subject to design). All 4 frontages activated.
| Assess impact on the character and appearance of the Conservation Area. | Strong positive impact on character and appearance of the Conservation Area | Minor positive impact on character and appearance of the Conservation Area | Neutral impact on character and appearance of Conservation Area, or negative impact |  | No improvement |  | Replace façade, roof and windows (as in Refurbishment option) |  | Replacement of low-quality existing podium building with high-quality design will enhance Conservation Area (subject to design) |  | Replacement of low-quality existing podium building with high-quality design will enhance Conservation Area (subject to design) |  | No material change to existing appearance |  | No material change to existing appearance |  | Replace façade , roof and windows |  | Replace façade , roof and windows |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Replacement of low-quality existing building with high-quality redevelopment will enhance Conservation Area (subject to design) |  | Replacement of low-quality existing building with high-quality redevelopment will enhance Conservation Area (subject to design) |  | Replacement of low-quality existing building with high-quality redevelopment will enhance Conservation Area (subject to design). Consideration given to proportions, massing, scale and materiality to complement context.
| Does the emerging option impact on LVMF viewing corridors? Yes/ No | LMVF viewing corridor not impacted | Minor impact on LVMF viewing corridor | LMVF viewing corner impacted |  | No change to height/massing |  | No change to height/massing |  | No change to height No impact on LVMF viewing corridor |  | No change to height No impact on LVMF viewing corridor |  | No change to height No impact on LVMF viewing corridor |  | No change to height No impact on LVMF viewing corridor |  | No change to height No impact on LVMF viewing corridor |  | No change to height No impact on LVMF viewing corridor |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | No impact on LVMF viewing corridor |  | No impact on LVMF viewing corridor |  | No impact on LVMF viewing corridor
| Appraisal against WELL criteria (seven concepts: air, water, nourishment, light, fitness, comfort, mind). | Greater than 70% WELL requirements have been incorporated in the design | Greater than 50% WELL requirements have been incorporated in the design | Less than 50% WELL requirements have been incorporated in the design | NB a full assessment will not be carried out at this stage and may not be appropriate depending on the option | Scope of work too limited to incorporate WELL requirements |  | Scope of work too limited to incorporate WELL requirements |  | Inherent constraints from the existing building might prevent to achieve more than 70% of the WELL requirements |  | Inherent constraints from the existing building might prevent to achieve more than 70% of the WELL requirements |  | Scope of work too limited to incorporate WELL requirements |  | Scope of work too limited to incorporate WELL requirements |  | Scope of work too limited to incorporate WELL requirements |  | Inherent constraints from the building might prevent to achieve more than 70% of the WELL requirements |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Unclear if 2018 design enable to achieve >70% of WELL requirements |  | As part of the 2020 it is possible to ensure the design is reviewed to achieve >70% of WELL requirements |  | As part of the 2020 it is possible to ensure the design is reviewed to achieve >70% of WELL requirements
| Compare options to assess permeability, connections, integration, urban greening and public realm benefits. | Strong positive improvement to the permeability, connections, integration, urban greening and public realm benefits. | Minor positive improvement to the permeability, connections, integration, urban greening and public realm benefits. | No improvement to the permeability, connections, integration, urban greening and public realm benefits. |  | No improvement |  | No improvement |  | No improvement |  | No improvement |  | No improvement |  | No improvement |  | No improvement |  | No improvement |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | An improvement on the existing condition with the inclusion active frontage which enhances the quality of the streetscape for pedestrians. However there are still elements of inactive frontage. |  | An improvement on the existing condition with the inclusion active frontage which enhances the quality of the streetscape for pedestrians. However there are still elements of inactive frontage. |  | Scheme far better integrated into locale All four frontages addressed, enhancing and reinforcing primary pedestrian routes with active use at ground level.
| Integrate Clean Air Villages Project Initiatives: Measure against the global policy of ’10 Healthy Street Indicators’. | Healthy Street indicators met to a sufficient level - Above 8 | Healthy Street Indicators met to a partial level - 5-7 | Limited number of Healthy Street Indicators met - under 5 |  | No change from existing |  | No change from existing |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | No change from existing |  | No change from existing |  | No change from existing |  | No change from existing |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | Above 8 indicators
Enable the development of a smart city | Appraisal against WIRED criteria (digital infrastructure) | PLATINUM/GOLD WIRED criteria met | SILVER WIRED criteria met | WIRED Certified or less | NB a full assessment will not be carried out at this stage and may not be appropriate depending on the option | No change from existing |  | No change from existing |  | Ability to install limited digital infrastructure |  | Ability to install limited digital infrastructure |  | No change from existing |  | No change from existing |  | No change from existing |  | No change from existing |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Ability to install limited digital infrastructure |  | Ability to install new digital infrastructure |  | Ability to install new digital infrastructure
Preserve and enhance local communities | Existing resident leaseholders offered the opportunity to stay in their homes or return to the development, should an option that requires this to be pursued | All existing residents leaseholders offered the opportunity to stay in their homes or return to the new development. | Resident leaseholders remain in situ with disruption | Existing resident leaseholders not given the opportunity to remain in their home or return to the new development. |  | Resident leaseholders can remain in-situ with disruption. |  | Tenants will be required to move out during the works however will be able to return on the works being completed. |  | All existing resident leaseholders offered the opportunity to stay in their homes or return to the new development. |  | All existing resident leaseholders offered the opportunity to stay in their homes or return to the new development. |  | Resident leaseholders remain in situ - with or without disruption. |  | Resident leaseholders remain in situ - with or without disruption. |  | All existing resident leaseholders offered the opportunity to stay in their homes or return to the new development. |  | All existing resident leaseholders offered the opportunity to stay in their homes or return to the new development. |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | All existing resident leaseholders offered the opportunity to return to the new development. |  | All existing resident leaseholders offered the opportunity to the new development. |  | Existing leasehold residents will be offered the opportunity return to the new development.
| Net additional residential floorspace against base position. | Net additional residential floorspace. | No change in residential floorspace | Loss of residential floorspace |  | Net additional residential floorspace. |  | Net additional residential floorspace. |  | Net additional residential floorspace. |  | Net additional residential floorspace. |  | No change. No net loss of residential floorspace |  | No change. No net loss of residential floorspace |  | No change. No net loss of residential floorspace |  | No change. No net loss of residential floorspace |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Net additional residential floorspace. |  | Net additional residential floorspace. |  | Net additional residential floorspace.
| Employment creation numbers associated with each option benchmarked against baseline (current position). | More than 0.3% of gross additional jobs as a proportion of the ward's employment | Between 0.1% and 0.3% of gross additional jobs as a proportion of the ward's employment | Less than 0.1% of gross additional jobs as a proportion of the ward's employment |  | 0% |  | 0% |  | 0.12% |  | 0.12% |  | 0% |  | 0% |  | 0% |  | 0% |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 0.17 |  | 0.17 |  | Voltarre to comment and review marking
Provide a mix of homes across all tenures including affordable provision | Assessment against market demand for private residential | Market assessment demonstrated a significant level of demand for private residential in this location | Market assessment demonstrated a partial level of demand for private residential in this location | Market assessment demonstrated a limited level of demand for private residential in this location |  | High level of residential demand. |  | High level of residential demand. |  | High level of residential demand. |  | High level of residential demand. |  | Not applicable |  | Not applicable |  | Not applicable |  | Not applicable |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | High level of residential demand |  | High level of residential demand |  | In line with market assessment
| Assessment against relevant WCC and GLA housing and affordable housing policies to create a mixed tenure development. | Scheme is fully Planning policy compliant with WCC and GLA policies in terms of private residential and affordable housing provision. | Scheme is partially planning policy compliant in terms of private residential and affordable housing provision (i.e.. does not comply with one of WCC or GLA policy) | Scheme is not planning policy compliant in terms of private residential and affordable housing provision (i.e.. Does not comply with WCC or GLA policy) |  | 10 new units. 1 Affordable Unit (80sqm). Compliant with WCC Policy S16. London Plan (inc. Affordable Housing & Viability SPG) would require 50% affordable housing on public land to follow the 'Fast-Track' route for scheme capable of delivering 10 units. |  | Assume the 2020 option would be compliant with WCC and GLA policy and provide 50% affordable housing. |  | 14 new units. No affordable housing. |  | Assume the 2020 option would be compliant with WCC and GLA policy and provide 50% affordable housing. |  | No affordable housing requirement |  | No affordable housing requirement |  | No affordable housing requirement |  | No affordable housing requirement |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 25% affordable housing compliant with current WCC policy S16, plus 2 protected tenancies. Adopted London Plan (inc. Affordable Housing & Viability SPG) would require 50% affordable housing on public land to follow 'Fast-Track' route. |  | Assume the 2020 option would be compliant with WCC and GLA policy and provide 50% affordable housing. |  | 50% affordable housing provision compliant with WCC planning policy (adopted and emerging), and London Plan. (Subject to agreement of tenure split with GLA)
Deliver a carbon efficient strategy that is environmentally sustainable | Operational energy - Improvement over Part L & Energy in Use Intensity (EUI) benchmarked against baseline conditions. Compliance with LETI | Exceed London Plan requirement of 35% improvement on Part L | Compliance with London Plan (i.e. 35% improvement over Part L) | Compliance with building regs |  | No M&E upgrade and no fabric upgrade |  | Only some fabric upgrade with the change of façade, window which would result in an improvement compared to 2018 scheme. However it is questionable whether this would be sufficient to achieve London Plan requirement |  | It is understood that the fabric would be upgraded and new heat pump and chillers would be installed. It is consequently anticipated to meet the London Plan requirement |  | It is understood that the fabric would be upgraded and new heat pump and chillers would be installed. It is consequently anticipated to meet the London Plan requirement |  | No M&E upgrade and no fabric upgrade |  | No M&E upgrade and no fabric upgrade |  | It is understood that the fabric would be upgraded, alongside the M&E system. It is consequently anticipated to meet the London Plan requirement. |  | It is understood that the 2020 option will have completely new M&E & fabric consequently it is within our gift to ensure we exceed London Plan standard requirements. There is also potential to explore compliance with LETI requirements |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | New fabric and new M&E consequently anticipated that operational energy target would be exceeded |  | New fabric and new M&E consequently anticipated that operational energy target would be exceeded. There is also potential to explore compliance with LETI requirements. |  | New fabric and new M&E consequently anticipated that operational energy target would be exceeded. There is also potential to explore compliance with LETI requirements.
| Circular Economy - Embodied carbon has been reduced against an agreed baseline or benchmark | Achieve 2030 LETI target 300 (Residential)-350 (Commercial)kgCO2e/m2 [A1 - A5] | Achieve 2020 LETI target 600kgCO2e/m2 [A1 - A5] | 1,000kgCO2e/m2 [A1 - A5] |  | The Building would be reused in almost its entirety with limited additional work which would result in only minor additional embodied carbon relatively. As a rule of thumb substructure and superstructure represent typically 70% of the A1-A3 emissions. |  | The Building would be reused in almost its entirety with limited additional work which would result in only minor additional embodied carbon relatively. As a rule of thumb substructure and superstructure represent typically 70% of the A1-A3 emissions. |  | Although the substructure and superstructure would be reused. The construction of the podium and the change of the façade is expected to push the embodied carbon emissions between 400-600kgCO2e/m2 |  | Although the substructure and superstructure would be reused. The construction of the podium and the change of the façade is expected to push the embodied carbon emissions between 400-600kgCO2e/m2 |  | The Building would be reused in its entirety with minimal additional work which would result in only marginal additional embodied carbon relatively. As a rule of thumb substructure and superstructure represent typically 70% of the A1-A3 emissions. |  | The Building would be reused in its entirety with minimal additional work which would result in only marginal additional embodied carbon relatively. As a rule of thumb substructure and superstructure represent typically 70% of the A1-A3 emissions. |  | The Building would be reused in almost its entirety with limited additional work which would result in only minor additional embodied carbon relatively. As a rule of thumb substructure and superstructure represent typically 70% of the A1-A3 emissions. The embodied carbon would be greater than Option 1 |  | The Building would be reused in almost its entirety with limited additional work which would result in only minor additional embodied carbon relatively. As a rule of thumb substructure and superstructure represent typically 70% of the A1-A3 emissions. The embodied carbon would be greater than Option 1 |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Business as usual for commercial building stands at 1,000kgCO2e/m2 and it is unlikely that much improvement over this target would have been achieved. |  | Business as usual for commercial building stands at 1,000kgCO2e/m2 and it is unlikely that much improvement over this target would have been achieved. |  | Business as usual for commercial building stands at 1,000kgCO2e/m2 and it is unlikely that much improvement over this target would have been achieved.
| Circular Economy - Qualitative assessment against on demonstrability and disassembly | Achieve 2030 LETI target: 50% reused | Achieves 2020 LETI target: 30% reused | 0% reused or It is unclear from the current design if this will be met |  | The building would be reused in almost its entirety - consequently the 50% target would be exceeded |  | The existing building would be reused in almost its entirety - consequently the 50% target would be exceeded |  | Most of the existing building would be reused - consequently the 50% target would be exceeded |  | Most of the existing building would be reused - consequently the 50% target would be exceeded |  | The existing building would be reused in almost its entirety - consequently the 50% target would be exceeded |  | The existing building would be reused in almost its entirety - consequently the 50% target would be exceeded |  | The existing building would be reused in almost its entirety - consequently the 50% target would be exceeded |  | The existing building would be reused in almost its entirety - consequently the 50% target would be exceeded |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Unclear if criteria will be met |  | Unclear if criteria will be met |  | Unclear if criteria will be met
| Circular Economy - Qualitative assessment against on demonstrability and disassembly | Achieve 2030 LETI target: 80% reusable Commentary on dismantlability | Achieve 2020 LETI target: 50% reusable Commentary on dismantlability | Not reusable or It is unclear from the current design whether this will be met. |  | Unclear if criteria met |  | Unclear if criteria met |  | Unclear if criteria met |  | Unclear if criteria met |  | Unclear if criteria met |  | Unclear if criteria met |  | Unnclear if criteria met |  | Unclear if criteria met |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Unclear if criteria will be met |  | Unclear if criteria will be met |  | Unclear if criteria will be met
| Water Resources - Consumption in I/per/year. Potable water reduction through greywater recycling and rainwater harvesting. | Less than 105 l/p/day. More potential for inclusion of greywater recycling and rainwater harvesting. | 105 l/p/day. Less potential for inclusion of greywater recycling and rainwater harvesting. | Exceeds 105 l/p/day |  | It is assumed that the new converted floor of the existing Development would have met the London Plan 2016 requirements (i.e. Policy 5.15 - 105/l/per/day). However the majority of the rest of the building would have most likely exceeded 105l/p/day |  | It is assumed that the new converted floor of the existing Development would have met the London Plan 2016 requirements (i.e. Policy 5.15 - 105/l/per/day). However the majority of the rest of the building would have most likely exceeded 105l/p/day |  | It is assumed that the Development would have met the London Plan 2016 requirements (i.e. Policy 5.15 - 105/l/per/day) |  | It is assumed that the Development would have met the London Plan 2016 requirements (i.e. Policy 5.15 - 105/l/per/day) |  | No upgrade to the sanitaryware and limited potential to retrofit greywater recycling |  | No upgrade to the sanitaryware and limited potential to retrofit greywater recycling |  | Anticipated that the water consumption would be less than 105l/p/day based on upgrade of sanitaryware throughout. In parallel, there will be potential to retrofit greywater recycling or rainwater harvesting |  | Anticipated that the water consumption would be less than 105l/p/day based on upgrade of sanitaryware throughout. In parallel, there will be potential to retrofit greywater recycling or rainwater harvesting |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Anticipated that the water consumption would be less than 105l/p/day based on upgrade of sanitaryware throughout. In parallel, there will be potential to retrofit greywater recycling or rainwater harvesting |  | Anticipated that the water consumption would be less than 105l/p/day based on upgrade of sanitaryware throughout. In parallel, there will be potential to retrofit greywater recycling or rainwater harvesting |  | Anticipated that the water consumption would be less than 105l/p/day based on upgrade of sanitaryware throughout. In parallel, there will be potential to retrofit greywater recycling or rainwater harvesting
| Biodiversity integration - Area of soft landscape created (m2) including green and living walls & urban greening factor (UGF) | UGF Above 0.4 achieved | UGF 0.4 achieved | UGF 0 | Urban Greening Factor is accounted for as a KPI in Biodiversity integration | As this is an existing building, it is more difficult to include high-quality soft landscape. In parallel, UGF is a requirement of the emerging Local Plan and consequently it is unclear whether this would have been met |  | As this is an existing building, it is more difficult to include high-quality soft landscape. In parallel, UGF is a requirement of the emerging Local Plan and consequently it is unclear whether this would have been met |  | UGF is a requirement of the emerging Local Plan and consequently it is unclear whether this would have been met |  | It would be expected that the Development attempts to achieve the emerging London Plan requirement of 0.4 UGF |  | Soft landscape is not part of this scope of work |  | Soft landscape is not part of this scope of work |  | UGF is a requirement of the emerging Local Plan and consequently it is unclear whether this would have been met |  | Potential to exceed UGF requirement |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | UGF is a requirement of the emerging Local Plan and consequently it is unclear whether this would have been met |  | Potential to exceed UGF requirement |  | Potential to exceed UGF requirement
Develop a financially viable option which considers the duty of the Council to deliver value for money | Option to demonstrate viability and deliverability for the Council, in line with WCC objectives of achieving value for money. | Scheme produces a positive Residual Land Value and 17.5% Profit on Cost targeted. Scheme is financially viable. | Scheme produces a positive of up to £5m. Residual Land Value and 17.5% Profit on Cost targeted. Scheme is financially viable. | Scheme produces a negative Residual Land Value. 15% Profit on Cost targeted. Scheme is financially unviable. |  | Financially viable and produces a positive residual land value |  | Financially viable and produces a positive residual land value |  | Financially viable and produces a positive residual land value |  | Financially viable and produces a positive residual land value |  | N/A not assessed previously |  | Financially viable and produces a positive residual land value |  | N/A not assessed previously |  | Financially viable and produces a positive residual land value |  | N/A not assessed previously |  | Financially viable |  | Financially viable and produces a positive residual land value |  | Financially viable and produces a positive residual land value |  | Financially viable and produces a positive residual land value.
| Cost and affordability to existing owners/occupiers. | Cost implication to occupiers limited to service charges arising from works completed. Any relocation costs fully covered | Cost of relocation is higher than is covered by CPO compensation code i.e. in sourcing equivalent property but is affordable by the resident using the full compensation package available | Cost of relocation is higher than is covered by CPO compensation code i.e. in sourcing equivalent property and this is not affordable by the resident even using the full compensation package available, requiring additional mortgage/borrowing. |  | Option will not increase costs for residents |  | Option will not increase costs for residents |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done |  | Cost implication to occupiers limited to service charges arising from works completed. Any relocation costs fully covered |  | Cost implication to occupiers limited to service charges arising from works completed. |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done |  | Amber rating as we can't assess what cost may be incurred by the resident until more work is done
Facilitate improvement of the quality of the public realm and reduce anti-social behaviour | Integrate Clean Air Villages Project Initiatives: Measure against the global policy of ’10 Healthy Street Indicators’. | Healthy Street indicators met to a sufficient level - Above 8 | Healthy Street Indicators met to a partial level - 5-7 | Limited number of Healthy Street Indicators met - under 5 |  | No change from existing |  | No change from existing |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | No change from existing |  | No change from existing |  | No change from existing |  | No change from existing |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | As per existing with some improvements on points: 8. Things to see and do: More active street frontage proposed 9. People feel relaxed: Proposed active frontages help with street safety and residents engagement with public realm |  | Healthy Street indicators met to a sufficient level - Above 8
| Secured by Design Assessment | All SBD criteria met | SBD criteria partially met | Limited SBD criteria met Not |  | No change from existing |  | SBD partially met on New Build portions of the façade |  | No change from existing |  | SBD partially met on New Build portions of the façade |  | No change from existing |  | No change from existing |  | No change from existing |  | SBD partially met on New Build portions of the façade |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Based on the current Approved Document Q (replaced Secured by Design in 2015) no immediate issues were found |  | Based on the current Approved Document Q (replaced Secured by Design in 2015) no immediate issues were found |  | EQ & Ownership Natural Surveillance Access Open space Lighting
| DDA Assessment | All DDA criteria met | DDA criteria partially met | Limited DD criteria met |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | DDA criteria partially met in the New Build sections of the development |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Based in the current Approved Part M current publication (updated in 2015) no immediate issues were found |  | Based in the current Approved Part M current publication (updated in 2015) no immediate issues were found |  | To be DDA compliant
| Consider/ assess front door locations for all/ any uses and street prominence/ connectivity | Design and Planning feedback concludes prominent front door/ street frontage locations for uses and enables connectivity with the wider area | Design and Planning feedback concludes prominent front door/ street frontage locations for uses and enables connectivity with the wider area, although further work required. | Failure to locate front doors/ design street frontages to increase connectivity with wider area. |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | New building with rationalised ground floor plan and front door access but all services to south with potential poor aspect to Orange Street |  | New building with rationalised ground floor plan and front door access but all services to south with potential poor aspect to Orange Street |  | All four frontages addressed, enhancing and reinforcing primary pedestrian routes and visual connection to front doors.
| Consider/ assess visual connection to and from neighbouring street/ public realm | Design and Planning feedback concludes excellent connections created with neighbouring streets and public realm. | Design and Planning feedback concludes good connections created with neighbouring streets and public realm. | Design and Planning feedback concludes limited connections created with neighbouring streets and public realm. Further work required. |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | No change from existing - very poor provision |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | New building with rationalised ground floor plan and front door access but all services to south with potential poor aspect to Orange Street |  | New building with rationalised ground floor plan and front door access but all services to south with potential poor aspect to Orange Street |  | Key corners and street views considered and articulated/ addressed
Minimise disruption for existing residents as much as possible | Identify a clear and detailed strategy that sets out the various options for existing residents being mindful of their individual circumstances. | Variety of options (including shared ownership) available to Resident Leaseholders and residents. Implemented early in advance of planning permission. | Limited options available to Resident Leaseholders and residents. | No opportunity for advance negotiations to acquire Leaseholder interests. No right to return. Any scheme proposed will cause significant and unavoidable disruption to residents |  | Council proposes to offer same standard as offered to residents of regeneration schemes |  | Council proposes to offer same standard as offered to residents of regeneration schemes |  | Council proposes to offer same standard as offered to residents of regeneration schemes |  | Council proposes to offer same standard as offered to residents of regeneration schemes |  | Council has not agreed to offer same standard as offered to residents of regeneration schemes where circumstances dictate that resident unable to remain in occupation during significant works |  | Residents do not have to move for this scheme, therefore Council has not agreed to offer same standard as offered to residents of regeneration schemes where circumstances dictate that resident unable to remain in occupation during significant works |  | Council has not agreed to offer same standard as offered to residents of regeneration schemes where circumstances dictate that resident unable to remain in occupation during significant works |  | Council has not agreed to offer same standard as offered to residents of regeneration schemes where circumstances dictate that resident unable to remain in occupation during significant works |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Council proposes to offer same standard as offered to residents of regeneration schemes |  | Council proposes to offer same standard as offered to residents of regeneration schemes |  | Council proposes to offer same standard as offered to residents of regeneration schemes
| Potential impacts on residents: Building work (noise, dust etc) | Relocations required are carried out with the minimum of disruption to residents as is practical | Relocations are carried out, but there is some disruption to residents lives as a consequence of the process. Suitable mitigations for vulnerable persons. | Residents subjected to significant levels of noise and dust throughout the project. Relocation causes significant and unavoidable disruption to residents lives. |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Residents do not have to move during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Unclear at this point if residents will be able to remain in residence during works. Residents will either be subjected to major noise and disruption of building works or require relocation |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Relocation will be required and this will result in disruption |  | Relocation will be required and this will result in disruption |  | Relocation will be required and this will result in disruption
| Potential impact on residents: Relocation | Options available to residents to remain in-situ. WCC Leaseholder Policy in Housing Renewal Areas implemented - including 'right to return' for Resident Leaseholders. | Residents required to relocate for a period of the redevelopment. | Residents required to relocate to alternative residence indefinitely. |  | Strong likelihood that residents will have to be temporarily relocated during the works |  | Strong likelihood that residents will have to be temporarily relocated during the works |  | Unclear at this point if residents will be able to remain in residence during works. |  | Unclear at this point if residents will be able to remain in residence during works. |  | Unclear at this point if residents will be able to remain in residence during works. |  | Residents do not have to move for this scheme |  | Residents will have to be temporarily relocated during the works |  | Residents will have to be temporarily relocated during the works |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Residents will have to be relocated to facilitate the works, but secure a full package of support from the council |  | Residents will have to be relocated to facilitate the works, but secure a full package of support from the council |  | Residents will have to be relocated to facilitate the works, but secure a full package of support from the council
| All secure tenants offered suitable alternative accommodation if required. | Tenants are found suitable accommodation that meets their requirements and assisted with the relocation process in a timely manner | Tenants are found suitable accommodation that meets most of their requirements and assisted with the relocation process in a timely manner | Tenants aspirations for rehousing are not possible to meet, resulting in the council having to take possession proceedings to secure vacant possession. The tenant will be housing in accommodation that they have less choice over and may not meet their requirements. |  | Unclear at this point if residents will be able to remain in residence during works. Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Unclear at this point if residents will be able to remain in residence during works. Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Unclear at this point if residents will be able to remain in residence during works. Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Residents do noave to move during works. Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Unclear at this point if residents will be able to remain in residence during works. Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment |  | Amber grading awarded as until housing need assessment completed we will not be able to make a robust assessment
Ensure that homes meet modern standards | Conformity with WCC and GLA requirements in respect of dwellings standards. Define no's egg al, more than 50%, less than 50% | All residential units in compliance with WCC and GLA dwelling standards | The majority of the residential units in compliance with WCC and GLA dwelling standards | A large number of the residential units are not in compliance with WCC and GLA dwelling standards |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Additional and retained residential units provisions do not fully comply with GLA standards (that also requires Part M compliance) |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Residential layouts design following current GLA London Plan |  | Residential layouts design following current GLA London Plan |  | Amenity area/ Part M 4 (2) & M4 (3)/ National Space Standards/ Storage allowance/ Current London Plan Generally e.g. overlooking/ daylight/ sunlight etc - daylight/ sunlight to be developed in Detail Design
Modern leisure, commercial facilities and homes | Proposed uses aligned with results of market testing for the mix of uses. | Proposed uses and design is completely aligned with the market assessments initial conclusions | Proposed uses and design is only partially aligned with the market assessments initial conclusions | Proposed uses and design is not aligned with the market assessments initial conclusions |  | High level of residential demand |  | High level of residential demand |  | High level of residential demand |  | High level of residential demand |  | Not completely aligned with market demand |  | Not completely aligned with market demand |  | Not completely aligned with market demand |  | Not completely aligned with market demand |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | High level of mixed use demand |  | High level of mixed use demand |  | High level of mixed-use demand
| Ability for proposed homes to be flexible i.e. WC compliant | All homes designed in line with accessibility requirements and level of WC homes provided in as per WCC policy | Majority of homes designed in line with accessibility requirements and level of WC homes provided in as per WCC policy 1/2 | Not all homes designed in line with accessibility requirements and level of WC homes provided does not meet WCC policy |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Existing residential unit provisions do not fully comply with WCC standards (that also requires Part M compliance) |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Residential layouts design following current AOD Part M (WCC requirement) |  | Residential layouts design following current AOD Part M (WCC requirement) |  | All homes designed in line with accessibility requirements and level of WC homes provided in as per WCC policy
| Ability for commercial uses to be flexible | Commercial Space offers flexibility | Commercial Space offers partial flexibility | Commercial Space offers no flexibility |  | Loss of commercial use |  | Loss of commercial use |  | No change from existing/ structure fl -fl inflexible |  | No change from existing/ structure fl -fl inflexible |  | No change from existing/ structure fl -fl inflexible |  | No change from existing/ structure fl -fl inflexible |  | No change from existing/ structure fl -fl inflexible |  | no change from existing/ structure fl -fl inflexible |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | 4m fl -fl provision |  | 4m fl -fl provision |  | Office space open plan and can be subdivided with generous floor to floor height allowance.
| Conformity with WCC policies on land use (including car park). Assessed against Policy S1, Policy S6, Policy S18, Policy S20, Policy S21, Policy S22, Policy S28, and TRANS 25 (excluding affordable housing policies (see above)) | Option Fully in compliance with WCC land use policy requirements (including car park) | Option in partial compliance with WCC land use policy requirements (including car park) | Option not in compliance with WCC land use policy requirements (including car park) |  | Loss of office use |  | Loss of office use |  | Uplift in residential. Uplift in office. Uplift in cinema. Adds retail. Decrease in parking acceptable, on the basis that existing car park experiences very low levels of demand and is underutilised. Mixed use policy (S1) residential requirement not triggered.** |  | Uplift in residential. Uplift in office. Uplift in cinema. Adds retail. Decrease in parking acceptable, on the basis that existing car park experiences very low levels of demand and is underutilised. ** Mixed use policy (S1) residential requirement not triggered. |  | No change to land use |  | No change to land use |  | No change to land use |  | No change to land use |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Uplift in residential. Uplift in office. Very minor loss of cinema (13 sqm). Additional retail. Decrease in parking acceptable, on the basis that existing car park experiences very low levels of demand and is underutilised.** Mixed use policy (S1) residential requirement not triggered. |  | Uplift in residential. Uplift in office. Very minor loss of cinema (13 sqm). Additional retail. Decrease in parking acceptable, on the basis that existing car park experiences very low levels of demand and is underutilised. ** Mixed use policy (S1) residential requirement not triggered. |  | Uplift in residential floorspace . Uplift in office. Uplift in cinema. Hotel and casino use acceptable in this location, subject to details of operational management. Loss of parking acceptable, on the basis that existing car park experiences very low levels of demand and is underutilised** Adopted Mixed Use Policy (S1) residential requirement not triggered.
| WIRED criteria met in respect of the building design | PLATINUM/GOLD WIRED criteria met | SILVER WIRED criteria met | WIRED Certified or less | Duplicate of Line 31 | No change from existing |  | No change from existing |  | Ability to install limited digital infrastructure |  | Ability to install limited digital infrastructure |  | No change from existing |  | No change from existing |  | No change from existing |  | No change from existing |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Ability to install limited digital infrastructure |  | Ability to install new digital infrastructure |  | Ability to install new digital infrastructure
| Conformity with WCC and GLA requirements in respect of dwellings standards. | All residential units in compliance with WCC and GLA dwelling standards | The majority of the residential units in compliance with WCC and GLA dwelling standards more than half | A large number of the residential units are not in compliance with WCC and GLA dwelling standards fewer than half |  | Additional and retained residential units provisions do not fully comply with GLA standards |  | Additional and retained residential units provisions do not fully comply with GLA standards |  | Retained residential unit provisions do not fully comply with GLA standards |  | Retained residential unit provisions do not fully comply with GLA standards |  | Existing residential unit provisions do not fully comply with GLA standards |  | Existing residential unit provisions do not fully comply with GLA standards |  | Existing residential unit provisions do not fully comply with GLA standards |  | Existing residential unit provisions do not fully comply with GLA standards |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | Residential layouts design following current GLA London Plan |  | Residential layouts design following current GLA London Plan |  | All residential units in compliance with WCC and GLA dwelling standards
| Consider daylight and sunlight matters for existing neighbours and amenity within the site, against the methodologies and criteria set out in the BRE guidelines (2011). | Most existing neighbouring buildings experiencing impacts within the BRE guidelines' recommendations (2011), with any shortfall of minor significance; Most of the proposed residential units and outdoor communal spaces meeting the BRE (2011) recommendations for daylight and sunlight, with any shortfall of minor significance. | Some of the existing neighbouring buildings experiencing impacts beyond those recommended by the BRE guidelines (2011), with limited impacts of major significance; Some of the proposed residential units and outdoor communal spaces falling short of the BRE (2011) recommendations for daylight and sunlight. | Most of the existing neighbouring buildings experiencing impacts beyond those recommended by the BRE guidelines (2011), with most of the impacts of major significance; Most of the proposed residential units and outdoor communal spaces falling short of the BRE (2011) recommendations for daylight and sunlight. |  | The proposed scheme will have no effect on the Daylight and Sunlight of the adjacent residential receptors. |  | The proposed scheme will have no effect on the Daylight and Sunlight of the adjacent residential receptors. |  | The proposed scheme will have some impact on the residential units adjacent to the site. The proposed residential units within the scheme will likely enjoy good daylight and sunlight amenity. |  | The proposed scheme will have some impact on the residential units adjacent to the site. The proposed residential units within the scheme will likely enjoy good daylight and sunlight amenity. |  | The proposed scheme will have no effect on the Daylight and Sunlight of the adjacent residential receptors. |  | The proposed scheme will have no effect on the Daylight and Sunlight of the adjacent residential receptors. |  | The proposed scheme will have no effect on the Daylight and Sunlight of the adjacent residential receptors. |  | The proposed scheme will have no effect on the Daylight and Sunlight of the adjacent residential receptors. |  | Not feasible to assess impact of future ownership |  | Not feasible to assess impact of future ownership |  | The proposed scheme will have some impact on the residential units adjacent to the site. The proposed residential units within the scheme will likely enjoy good daylight and sunlight amenity. |  | The proposed scheme will have some impact on the residential units adjacent to the site. The proposed residential units within the scheme will likely enjoy good daylight and sunlight amenity. |  | The proposed scheme will have some impact on the residential units adjacent to the site. The upper floors cutback from the southern elevation will likely result in improved retained daylight and sunlight amenity for neighbouring properties in comparison to previous option 7 iterations. The proposed residential units within the scheme will likely enjoy good daylight and sunlight amenity.
*Where legal requirements, whether via statute, policy or otherwise apply to matters covered in the definition of measurable outcomes, compliance with those obligations will be considered when assessing the outcome.
**It should be noted that the data referred to was provided by Q-Park to WCC in confidence and is commercially sensitive and not available for review.