## Slide 1
6 JUNE 2023
SCOTTISH TOWERS
INTRODUCTORY MEETING
(AB108)

## Slide 2
AGENDA
Introduction
01
Where we are
02
Decarbonisation
03
02
Resident focused service
04

## Slide 3
AXIS
Established
Ownership
Turnover
Staff
Offices
Credit rating
Values led
Fleet
1986
Family
£245m
1,000+
7
5A 2
8 values
450+
03

## Slide 4
AXIS
years
5
Construction
partnering
04

## Slide 5
SCOTTISH TOWERS
05
Set up a team of Senior Managers
Protection fan around the base of the blocks
Split project to external and internal
Early April

## Slide 6
SCOTTISH TOWERS
EXTERNAL
Scaffold Marc Jeffrey
Topographical Survey, Complete
Utilities Survey, Complete
Scaffold Designer Engaged, Design back 9th June
Ready to tender 12th June
Masonry Lee Convington
Structural Engineer Engaged, 4th April
Concrete Testing Complete, 9th April
Schedule of Repairs Complete, 16th April
New Building Regulations Implication's included (Grit Blasting )
Ready to tender 12th June
Windows Lee Convington
Specification agreed 12th April, Complete
Installations issues around Gas & Central Heating
Ready to tender 12th June
06

## Slide 7
SCOTTISH TOWERS
INTERNAL
Fire doors Marc Jeffrey
Specification agreed
Need to carry out a full intrusive survey, (To start in the next few weeks )
Decorations Marc Jeffrey
Specification agreed
Measured
Ready to tender 12th June
Floor finishes Marc Jeffrey
Specification agreed
Asbestos testing, awaiting
Ready to tender 12th June
Mechanical & Electrical
Dan Sams
Full Design Complete 30th May
Project Scheduled out into components and quantities
Ready to tender 12th June
07

## Slide 8
CONSULTANTS
08
JAMES MELLING Mellingbuild
GEORGE CHARALAMBOUS T&T Consultants
DUNCAN MCAPLINE Furness Partnership Consulting Engineers

## Slide 9
SCOTTISH TOWERS
DECARBONISATION
MAIDA VALE

## Slide 10
EXPERIENCED & INNOVATIVE
MANAGEMENT AND TEAM
Alan Noble
M&E Director
Team lead for Axis’ M&E Division with over 35 years experience, including:
H&V News - Industry Awards Judge for Innovation and Technologies
Carbon Energy Saving Technology
Design and Build Domestic, Commercial and District Heating Systems, Hybrid Communal Systems, Retrofit designs.
Gas Compliance Programmes
Electric Compliance Programme
Water Hygiene Works
Responsive Contracts Management in all M&E Discplines

## Slide 11
SCOTTISH TOWERS (AB108) INTRODUCTORY MEETING
SOLAR WALL
REDUCING ENERGY TO COMMUNAL AREAS

## Slide 12
ELECTRIC VEHICLE CHARGING
FREE STANDING POINTS
12
Combination of all charge points available working with our partners, with billing systems available.
12

## Slide 13
PACKAGE PLANT SOLUTION
ROOFTOP OF GROUND LEVEL
13
Applications include:
Low Temp Hot Water (LTHW)
Medium Temp Hot Water (MTHW)
Chilled Water (CHW)
Energy Centers
Battery Storage
13

## Slide 14
ROOFTOP HYBRID COMMUNAL
WITH HIU AND UNDERFLOOR HEATING
14
Features and benefits:
Air Source Heat Pumps
Solar PV
Energy Saving Communal areas
Reduced Energy Demand from the Grid
No Radiators taking up space
HIU – removes Gas from the building
14
14

## Slide 15
A RESIDENT FOCUSED SERVICE
OUR RESIDENTS MATTER

## Slide 16
Residents and leaseholders must be at the heart of everything we do

## Slide 17
Patricia
Kemeisha
Kemara
RESIDENT LIAISON TEAM
Our RLOs are your first point of contact and will be onsite when work is taking place
…here to answer your questions, help those who need assistance and make sure the work meets resident’s satisfaction

## Slide 18
CLEAR COMMUNICATION
We aim to build a close relationship with residents and keep you informed of progress throughout the project.
OUR RESIDENTS MATTER
…so you are comfortable with the work taking place around your property
We have a number of communication tools…

## Slide 19
Receive latest announcements
Find out about resident events
Book appointments
Keep up to date with the project’s progress
See photos of what the team are up to
Find answers to frequently asked questions
Contact the team
…inc live chat (during working hours)
RESIDENT APP
Let’s stay connected…
19

## Slide 20
THANK YOU