## PRIORITY A
Action Plan 2017-2022 |  |  |  |  | Action Plan 2023 - 24
Priority A: Where it is possible for us to do so, prevent people from rough-sleeping in the first place |  |  |  |  | Priority A: Where it is possible for us to do so, prevent people from rough-sleeping in the first place
Our Objectives | Our New Commitments | Responsibility of | Progress at 31 December 2022 | Comments | Our Objectives | Our New Commitments | Responsibility of | Update at 2023/24 | Comments
Fewer people find themselves sleeping on Westminster's streets | We will learn from our on-going pilot and use this to shape a new specialist, frontline service for single vulnerable people at risk of rough sleeping with recognised local links to Westminster as part of our re-designed housing options service | Growth Planning & Housing (GPH) | WCC achieved successful funding opportunities through DLUHC RSI 4 to deliver a pilot NSAP programme that further developed the frontline model of delivery for rough sleepers. Improving the assessment & triage approach and access to private rented sector housing. This service was complemented by the existing assessment centres at Harrow Road & the Passage. |  | Fewer people find themselves sleeping on Westminster's streets | WCC achieve 3 year funding RSI 22-25 to continue the Rapid Triage and Assessment (A & T) model from the NSAP pilot delivered within Rsi 4 | Growth Planning & Housing (GPH)
| We will lobby the Mayor and the government to ensure that other areas are supported to stop people from coming to Westminster in the first place and getting the help they need closer to home | PPC/(KM in conjunction with JT) | Feb 2022 the Government published the update on the Vagrancy Act, which was due to be repealed through the Police, Crime, Sentencing and Courts Act 2022, as part of the government's commitment to end rough sleeping. Department for Levelling Up, Housing and Communities (DLUHC), however have now withdrawn the placeholder they had to repeal the Act to give themselves longer to consider whether to replace the Act (and if so with what). In the interim, the Vagrancy Act will remain in force. WCC continue to review this position and completed walkabouts with Civil Servants in 2022 who had a particular focus on the policing aspects of rough sleeping. They used this visit to inform Ministers on the challenges currently facing Local Authorities around policing and rough sleeping, which will hopefully result in revised national guidance to ensure a consistent, effective and compassionate approach. WCC Policy & Innovation team had regular contact and meetings with the Home Office between 2019-2022. |  |  | WCC continues to monitor the impact of the repeal of the Vagrancy Act 1824: Police, Crime, Sentencing and Courts Act 2022. March 2023, 'Action Plan to crack down on anti-social behaviour' will be monitored and reviewed by WCC policy team, PPL and Housing Needs. | GPH
People who are released from prison discharged from hospital or other institutional settings do not end up on the streets | We will draw on the learning from the No First Night Out pilots in other London boroughs to develop and implement approaches such as rapid assessment and intervention for people before they spend a night on the streets. | GPH | The Passage launched the pilot 'No night out' a model of services targeted at people new to the streets and support people to find and sustain a home for good in 2021/22. |  |  | The Passage receive 3 year funding RSI 22-25 to continue the 'No Night Out' model | GPH
| We will ensure that preventative work begins at the earliest point possible and develop an action plan for joint implementation to help reduce the number of those sleeping rough after leaving institutional settings | GPH | Ending Rough Sleeping Workshop August 2021 and a second Strategic workshop in January 2023 with over 30 providers invited to support the Council in the overview of the strategic direction of services from 2021-2022 and the submission of the 3 year funding package by Government 2022-2025. Year 4 RSI 2021-2022 funding allocated following bids submitted by WCC in 21/22 achieved £5,299,469 and an increase of £1,074,349 of funding allocated in 2020/21. WCC further developed the action plan and joint implementation of projects during 2021/22. This funding secured the services of the rough sleeping team to increase the focus on the areas of substance and alcohol dependency and the work with specialist partners in these fields who support our rough sleeping clients. In addition, increasing capacity within the system for mental health assessments and support, together with the opportunity to continue our ongoing work to support rough sleepers during the pandemic, our collective success made a major contribution to the focus on an early intervention and a preventative approach for the future as well as tackling immediate needs. This includes ensuring that people are prevented from becoming homeless at points of service intervention such as discharge from care, hospital, or prison and the continued approach based on personalisation and localisation of services. |  |  | Rough Sleeping is particularly acute in Westminster, and we manage by far the highest number of rough sleepers in the country. Westminster City Council and our partners continue to demonstrate national leadership in the delivery of rough sleeping services, investing millions each year to provide both accommodation and support services, to ensure every rough sleeper in our City receives the best individually tailored route away from the street. The volume and specific challenges we manage here are unlike any other with a highly transient population of non-UK national rough sleepers who have support needs but sleep on our streets for different reasons; a high number of ‘returners’ (habitual rough sleepers who may disappear for periods but periodically return to sleep in Westminster); a core of long-term entrenched individuals; in addition to a number of people who have accommodation and are receiving support but due to complex needs return to the streets during the day. There is more we, our community, and our partners want to achieve together during 2023-24. Working closer than ever before with a commitment to deliver our services through the 3-year funding package of Rough Sleeping Initiative (RSI) 22-25 we will further embed the lived experience and voices of our service users to help us take a system wide view of service delivery and build a new multi-disciplinary model of governance (across Housing, Voluntary Services, Health, Safeguarding, and Enforcement) with shared ownership and accountability. Priorities from 2023 include: WCC, and their providers of commissioned services to maximise the delivery of funding achieved in the RSI 2022-25 allocation to Westminster City Council in securing £21,529,188. | GPH
| We will build an understanding of individual offenders history or risk of rough sleeping into the services we commission to tackle prolific offenders through the Safer Westminster Partnership and funded by the Mayors Office for Policing and Crime (MOPAC). This will evolve over time as the approach taken by MOPAC to funding 'commissioned' services becomes clearer. | GPH/PPL | In 2021 - WCC & K & C respond through a MOPAC forum to the Mayor of London consultation document 'Support for survivors of domestic abuse and their children in safe accommodation' and develop our bi-borough strategy on supporting the survivors of DV, meeting the diverse needs of survivors, particularly around race and, ability and LGBT. Local needs assessments highlighted the increase in multiple disadvantage, particularly around substance use and mental health. Securing safe accommodation for this group is challenging. The strategy adopted a whole housing approach, where the whole housing sector is equipped to meet the needs of survivors. Addresses all housing tenure types and the full range of housing needs those experiencing domestic abuse will have. In this way, survivors will have the best and consistent housing support across their journey. The strategy reflect the wider role that the housing sector can play and should follow best practice. |  |  | WCC to make applications for additional grant funding available for MOPAC services during 23-24. | GPH
| We will improve how we prevent short sentence prisoners who have a history of rough sleeping, or who have been in a hostel from returning to the streets upon release from prison, by working with the CRC and directly with prisons to ensure continuity of support and reducing confusion. | GPH | In April 2021, the Department of Levelling Up, Housing and Communities (DLUHC) notified Local Authorities in England of £13 million available to bid for a Accommodation for Ex-Offenders (AFEO) funding programme. DLUHC recognised circa of 53% of rough sleepers had also spent some time in prison. They also recognised that a significant proportion of ex-offenders did not meet the ‘priority need’ criteria as statutory homeless applicants, which often limited their housing options post-release. WCC were awarded £207,000 with at March 2022 - 51 ex-offenders having moved into a new home via the AFEO and the scheme, achieving 43 of those tenancies still sustained. |  |  | WCC to make applications for additional grant funding available for ex-Offender funding during 23-24. | GPH

## PRIORITY B
| Action Plan 2017-2022 |  |  |  |  | Action Plan 2023 - 24
| Priority B: Supporting people to rebuild their lives |  |  |  |  | Priority B: Supporting people to rebuild their lives
Line 5 | Our Objectives | Our New Commitments | Responsibility of | Progress at 31 December 2022 | Comments | Our Objectives | Our New Commitments | Responsibility of | Update at 2023/24 | Comments
6 | All who find themselves on Westminster streets are identified quickly and have their needs accurately assessed | We think that giving more time to working intensively with a person to understand their needs, and helping to find the right solution for them at the beginning of our engagement, is more likely to be successful in preventing them from becoming homeless again. To do this we will commission a new assessment centre where rough sleepers can be referred for an extended period of assessment to prevent them becoming entrenched. They will be able to stay there for up to 30 days while they have their needs assessed and will be helped to find the most appropriate solution. Any particular needs around mental health and substance misuses an be accurately assessed and a plan put into place to address those needs. We already secured over £60k in external funding through the DCLG to invest in the development of the assessment centre. | Growth Planning & Housing (GPH) | Funding through RSI 4 2021/22 enabled the expansion of the Street Outreach provision through the Assessment & Triage (A & T) model developed to move rough sleepers quickly from the streets into emergency accommodation and a planned move-on offer. WCC have worked during 2021/22 to develop and link into the Pan-London approach and work to developing greater cooperation and work between our local authority borders and a collective approach to managing the transient nature of rough sleepers and this work will also focus on NRPF clients. During 2021-22 WCC further develop our work within the assessment centres of the Passage and Harrow Road, ensuring the offer to rough sleepers is consistent, responsive and achieves effective move-on options. In 2021/22 WCC Charitable Trust supported funding to Pimlico Angels with a project aimed to deliver a twice weekly outreach in the South of Westminster, providing hot, home cooked meals for those who would not otherwise be able to access them targeting those who do not have access to public resources. Pimlico Angels provide access to basic necessities such as clothing, toiletries and note circa of 50 people access this service each week. | https://officesharedservice-my.sharepoint.com/personal/hclarke_westminster_gov_uk/Documents/Desktop/Street%20Count%202022.pdf |  | Funding has been used to establish or continue Rough Sleeping Initiative services agreed by DLUHC to immediately intervene in, prevent and reduce rough sleeping in fiscal years 2022/23 to 2024/25. Breakdown of funding has been agreed Year 1 - £6,434,761; Year 2 - £7,626,116; Year 3 - £7,468,311; Final Sum of Total - £21,529,188. With the aims to Prevent rough sleeping, access rapidly those sleeping rough for assessment and triage, provide a wide range of high-quality accommodation with support, deliver a rapid response during periods of cold weather or other emergencies that also lead to sustained moves off the streets, develop and deliver pathways out of rough sleeping services into the community, deliver a wide range of complementary mental health, substance misuse, primary healthcare etc. services that reflects the particular needs of rough sleepers, sustain those moves through delivery of community-based services and access into employment. | Growth Planning & Housing (GPH)
7 |  | We will introduce a new person-centred assessment and referral process which will be used by all agencies working with a rough sleeper across the sector. This will help simplify and streamline the process for rough sleepers and agencies. It will also facilitate the sharing of information about those being helped and the support they have been provided with at all stages of the process | GPH | 2021-22 WCC review the referral processes to assess rough sleepers and the street population access to services and the gateways to their transition into securing longer term accommodation options. |  |  | Assessment Centres: WCC will continue to commission two: centres Harrow Road Assessment Centre (HAC) and Passage House Assessment Centre (PHAC) these service operate to provide self-contained accommodation within each centre for circa of 60 days, with a move on route identified but some more intensive work is required with the person in which to achieve this and supported by onsite staff available 24 hours a day. across 81 units of accommodation between both centres.​ | GPH
8 | Every rough sleeper is offered a personalised and sustainable route away from the streets, based on their circumstances | We will provide an enhanced reconnection service to UK residents who need it. Additional support will be provided to vulnerable people who are being reconnected to their home area, linking them into support and services they may need. We have partnered with the GLA to deliver this through a new service funded by the DCLG | GPH | Two Assessment Centres – Passage House and Harrow Road continue to deliver co-production with people with lived and professional experience which must take a central place in service and strategy design, delivery, and commissioning. Both centres developing their with people presenting as homeless on the streets of Westminster to ensure advice and support is consistent. Working closely with those who have unsettled status to offer support and options to their decisions to return to their home country. Services ensure that all clients has been informed of the EU settlement Scheme and offered an immigration advice assessment with a registered adviser. All clients supported to reconnect outside the UK are first offered the opportunity to speak to an immigration adviser in order to make an informed decision. This also applies to clients who want to reconnect even if they have entitlements in the UK. |  |  | Rapid Assessment, Triage & Accommodation (RATA), will also be funded from the learning of the pilot in 2021/22. The RATA targeted to people to enable effective assessment, triage and short stay accommodation, circa of 30 days, where a move-on option plan identified and agreed with the rough sleeper but requires a short time to put this into place. This plan will include accommodation, access to training and employment, support with language barriers and access to professional immigration advice.​ Emergency bed spaces will also be available across the rough sleeping and mental health pathways that accommodates clients from the streets during SWEP. This emergency response for rough sleepers to preserve their safety and wellbeing during severe weather conditions. It is activated by the GLA if the forecast is below 0°C in London. SOS outreach teams work diligently with clients as part of the In for Good Principles to explore move on options and prevent a return to the street. | GPH
9 |  | We will re-commission our accommodation services for rough sleepers in the city looking to build in new ways of delivering services based on outcomes and introduce a small payment-by-results element to contracts and more opportunities for local involvement. We will work with out partners in the sector to deliver this approach - in particular to think together about new ways we can do things. We don't have all the answers; our focus will be on encouraging ideas and solutions form the experts who work with people on the frontline. | GPH | Two Housing First scheme – Solace (specialists in VAWG) and St Mungo’s phase 2. In November 2022 we were given the opportunity to bid for an extension to the scheme from April 2023 to March 2025. DLUHC made it clear in their prospectus that joint bids between LAs would be welcomed, so WCC submitted a bid alongside RB Kensington & Chelsea and Hammersmith & Fulham. The primary reason for the tri-borough bid was to mirror the arrangement of our shared Probation Service. During 2022, WCC introduce specialist services through the provider network to deliver services to our Roma communities identified in the street counts with a high presence on the streets supporting 10 bed spaces during 2021-22 who meet this cohort. The Covid response during 2020-22 required LAs to review a number of their processes and the 'Everyone In' delivery directed by Government. WCC achieves £ 5,299,469 in 2022 to support rough sleepers who are vulnerable to Covid through the Protect & Vaccinate programme of work. Expansion of health and wellbeing events to encourage health check-ups/vaccination take-up, expansion of Vaccine Deployment Programme to rough sleepers in all settings. Training support to staff in all settings to increase vaccine take up and Hotel Accommodation Subsistence Provision and an offer of accommodation to support the vaccination offer to rough sleepers. Circa 60 rough sleepers take-up accommodation offers and circa of 500 clients in supported accommodation (former rough sleepers) have access to support and the vaccination programme. |  |  | WCC will review the Single Homelessness Accommodation Programme (SHAP) funding during 2023 with the aim to submit capital and revenue funding bids to the GLA to support the expansion of WCC Housing First Offer to clients. | GPH
10 |  | We will explore the use of multi-disciplinary team models when re-commissioning both our outreach teams and accommodation services. These will bring together experts and professionals to tackle the various issues associated with rough sleeping that often need specialist support, including physical and mental health, immigration and housing advice. We are keen to develop difference services models to increase changes for people to make changes. | GPH | Direct support for people with multiple needs and help them to successfully access and navigate the complexity of health and treatment structures as well as promoting the importance of good health and emotional wellbeing. Holistic Trauma Support for Male Survivors of Sexual Abuse, trauma-informed therapeutic contact and interventions that are tailored to the client’s needs, meeting the client ‘where they are at’ rather than pathologizing their situation. It is available to clients across all of our pathways and the service has capacity for flexible referral numbers. The universal offer across the pathway includes regular training and a trauma advice clinic for workers and will be embedded within the key working teams, across our RS offer and provides key engagement for those who can be marginalised. Enhanced partnerships with health services to develop understanding and support for those recovering from trauma. |  |  | WCC successfully achieved funding in 2023 through the Office for Health Improvement & Disparities (OHID) - SSMTR – Housing Support Grant 23 – 24. This funding is being granted to local councils on a 'test and learn' basis, to grow the evidence base on both the housing related needs of people in treatment and effective housing interventions. Improve the rate of recovery from drug and alcohol dependence for people in structured treatment; Reduce the rate of unplanned discharge from treatment for people with a housing need Improve access to, and sustainment of, suitable accommodation for people engaging in structured drug and alcohol treatment; Reduce the scale of unmet housing need for people in structured drug and alcohol treatment; Build the evidence base on the housing related need for people dependent on drugs and alcohol and the most effective interventions. Housing Needs will develop a number of initiatives that include Floating support workers who will have specialist knowledge around drugs and alcohol dependence and provide support to people in their homes to improve their engagement in treatment services. Training, personal development and workforce support. 3-year allocation of funding led by Public Health – Total funding £1,799,885.65 | GPH
11 |  | By linking in with Westminster's wider employment service offer, we will ensure that those service users who are ready to work are given the opportunity to move towards employment as a lasting route away from the streets. We will also do this by enabling more people in our accommodation services to volunteer and gain work and life skills through this route. To help deliver on this we will make seed funding available for projects that offer new ways of supporting rough sleepers, with a focus on those that can help people build up life skills, such as literacy and numeracy designed to be attractive and accessible to clients | GPH | Increased mental health professionals outreach capacity. In 2021/22 The Passage and the Goring Hotel School offered placements to rough sleepers wishing to work in the hospitality industry and teaches hospitality skills to people who have experienced homelessness or significant barriers into employment. A community collaboration between London's hospitality sectors, the Council and homelessness sector. |  |  | During 23/24 WCC will ensure the service offer delivers on the multi-agency partnership approach, a well-developed network of specialists which includes access to Drug and Alcohol services, a pathway for people experiencing homelessness into structured drug and alcohol treatment, detoxification and rehab and hard reduction services. Peer Advocacy supporting engagement with health and care appointments and services, practical support with follow ups, helping individuals navigate across the system, increasing knowledge skills and confidence in their own health, linked to an ongoing Vaccinations and Health protection offer and the wider health and wellbeing of our rough sleepers making every contact count. Mental Health triage into MH services and pathways, specialist services including the Joint Homelessness Team and links to Primary Care inclusion Health practices, ensuring all rough sleepers can register with a GP. Community Health services that include in-reach nursing teams who attend services. Westminster and Camden deliver a joint service offer with a hotel planning the expansion to establish a dedicated ‘Hospitality Training School’ within the hotel to work with rough sleepers as part of their move-on from the emergency provision. The hotel is in discussion with options to convert some areas of the hotel for ‘permanent’ accommodation linked to employment and training opportunities during 23/24. | GPH
12 |  | We have developed a Housing First pilot in partnership with a registered provider and recognise its potential benefits. The outcomes from the pilot will be analysed and further Housing First approaches will be explored and commissioned without our new outreach contracts if it proves successful. | GPH | Housing First Programmes in WCC have been commissioned in Westminster by since 2017 but expanded during 2021-22 with further funding. There are two separate housing led schemes, Multi-gender scheme delivered by St Mungo’s and a Specialist women’s scheme delivered by Solace for clients experiencing domestic abuse and VAWG. 64 clients across both Housing Led schemes, part of a diverse portfolio of accommodation options for our most complex and entrenched rough sleepers. Partner with several Housing Associations who work directly with the support provider to enable flexible sign-up opportunities and respond to tenancy issues in a trauma informed way. |  |  | WCC will review the Single Homelessness Accommodation Programme (SHAP) funding during 2023 with the aim to submit capital and revenue funding bids to the GLA to support the expansion of WCC Housing First Offer to clients. | GPH
13 | Improvements in the health and well-bring of rough sleepers with a particular focus on addressing mental health and substance misuse issues | We will work with our CCG partner to take forward the commitments to rough sleepers contained in our Joint Health and Wellbeing Strategy | GPH | In 2021 WCC support and work to develop the St Thomas’s detox. This provision meets a gap for patients who are rough sleeping with complex physical health needs. Residential rehab programmes, Rapid prescription services, PHE Rough Sleeping Drug and Alcohol Grant has significantly increased provision of specialist substance misuse navigators, consultants time. |  |  | As section 10 | GPH
14 |  | We will work with the NHS and specialist services to expand on a 'pre-treatment' approach, bringing NHS services to people who may find it difficult to access and engage with mainstream therapy and treatment. We will build on pilot projects already underway to trial this approach, such as drop-in counselling and problem gambling and anger management of support services | GPH | A collaboration with the North London Sub Region to add additional accommodation and pathways options for rough sleepers in Westminster A psychological informed environment, with trauma informed care. In practice: attention given to the physical environment, as well as language and all support planning/case management systems. A strengths based approach with strong emphasis on co-production with clients. Development of a psychological framework for all service delivery, reflective practice and staff development. This includes commissioning South London and Maudsley NHS Trust to work with WCC to develop advocacy and development work on treatment services and on services for women experiencing severe and multiple disadvantage. Strong emphasis on partnership working through “health” relationships and the Westminster Homelessness Partnership (WHP). |  |  | Funding to support SLaM approved through RSI 22-25, In partnership with South London and Maudsley as the lead innovator for Psychology in Hostels project [PiHs] Clinical Psychologists are embedded across the supported housing pathways to deliver training for staff and provide individual and group psychological therapy to better meet the needs of homeless people who can have histories of complex trauma, difficulty trusting and engaging with services. The services include delivering added value to this investment with the common aim of reducing rough sleeping at the centre of the capital. This approach ensures that each individual has an individually tailored plan to move away from rough sleeping and sustain this move, the vast majority of people who find themselves sleeping rough do not spend a second night sleeping out, services are provided to a highly transient population of non-UK national rough sleepers, responses to individuals who periodically return to rough sleeping are focused and co-ordinated. | GPH
15 |  | We will find new ways of working with people who revolve in and out of our services, including the introduction of trial runs in our supported accommodation or training flats to help build confidence | GPH | WCC submit and successful RSAP funding 2021/22 grant submitted for - £1.31m with WCC contributing £874k to acquire 10 properties for move-on accommodation as emergency units with wrap around support for each person. Rough sleepers to be accommodated for up to 2 years with a move-on plan beyond. |  |  | WCC will build on the RSAP funding 21/22 and submit a funding request for accommodation through the SHAP programme in 2023. | GPH
16 |  | We will commissions a new specialist service aimed at helping those who accommodation placements repeatedly break-down and who are regularly excluded from other services | GPH | WCC submit and achieve £3.2m 3 year funding through DLUHC Changing Futures Programme to address multiple disadvantage and system failures for people in Westminster. Proliferation of service providers from a range of different disciplines endeavouring (and sometimes struggling) to work together effectively. Large numbers of service users, many of whom face severe and multiple disadvantage. Multi-agency partnership including ASC, Family Services, Safeguarding teams, St Mungo's, WLM, Connection, Turning Point, Health and Homelessness Service, The Passage, CSTM, SHP. Systems thinking methodologies and experiences by others (e.g. the Big Lottery Fulfilling Lives projects and the MEAM experience) and our learning from the Covid Pandemic. Cross-organisational team sharing issues, plans and change in order to identify the issues across our “system” of support that are impeding our efforts. Governance fed into a strategic group from homelessness, substance misuse, mental health, adult social care etc to review learning arising from the action experiments to drive forward systemic change through commissioning, strategy or key operational changes. |  |  | Changing Futures funding extended for a further 1 year until 25-26 | GPH
17 |  | We will ensure our services respond to the psychological and emotional needs of rough sleepers by ensuring every service meets the Psychologically Informed Environment (PIE) standard and that this is monitored consistently. | GPH | WCC commissions SLaM PiH during 2021-22 to deliver services to those who experience Sexual abuse, Physical abuse, Neglect, Five key areas of psychological framework, environments, staff training & support, managing relationships, evaluating outcomes. Evidence-based best practice for homeless and accommodation services to address the unmet psychological needs and trauma that precede, accompany and perpetuate homelessness, chaotic lifestyles, long-term MH and criminal justice. Interventions include direct and indirect therapy, training and reflective practice across Westminster. |  |  | As section 14 | GPH
18 |  | We will explore new routes into treatment services for rough sleepers in accommodation services. A new service for local people who have a dual-diagnosis has recently been launched and the success of this will be monitored and assessed | GPH | As above |  |  | As section 14 | GPH
19 | Female rough sleepers are supported in a manner which is appropriate and sensitive to their needs | A range of services will be re-modelled to provide more spaces to meet the needs of female rough sleepers: 2 services will be remodelled to accept women and their dogs; one will be remodelled to specialise in providing move on for stable couples and a short term training flat will be created | GPH | RSI 4 funding during 2021-22 secured funding for the provision for rough sleepers who are women and transgender clients and experience multiple disadvantage and complex needs. Housing Needs support the MARAC lead for VAWG and multiple disadvantage. In 2021 WCC develops our Violence Against Women & Girls Strategy 2021 - 2026. |  |  | WCC secured RSI 22-25 funding for specialist women’s provision to support Women experiencing homelessness and face multiple disadvantage, including domestic abuse and VAWG. ​Our services are inclusive for LGBTQI+ community. The funding will support the expansion of services to address changes in legislation for victims of Domestic Abuse all victim/survivors of DA are considered in 'priority need' for homelessness assistance. Services include The Marylebone Project provides support and 30 bedspaces, including 5 for no recourse to public funds women, for rough sleepers. General Needs beds accessible for those who are assisted through statutory homelessness duties. Rough Sleeping Services include Westminster Women’s Safe Space (WWSS) Rapid access safe space with 16 short-stay beds for complex rough sleepers experiencing VAWG and multiple disadvantage. Housing First Specialist VAWG and domestic abuse Housing First programme currently supporting 30 women. Westminster Women’s Refuge 35 beds for women. | GPH
20 |  | Improved joint working will be put in place with the domestic violence charitable sector and funding will be sought from dedicated funding streams for a female only emergency 'safe space' overnight options to ensure that we do not miss windows of opportunity with very vulnerable female rough sleepers. | GPH | The Sanctuary is the first and only centre of its kind in the UK, where the doors are always open. This always-open policy means that women working but struggling to stay off the streets will have a safe place to go outside of regular working hours. It also means that the increasing number of women experiencing domestic violence have somewhere to go during a crisis. At The Sanctuary, women help and nurture women, providing safety and support. In addition to essential services, such as family mediation, landlord negotiation and assisting women in finding private sector accommodation, women can also access training and education, advice, holistic wellbeing classes, plus practical facilities including a clothing store, laundry, showers and food banks. |  |  | As section 19 | GPH
21 |  | A pilot will be developed to embed practical techniques to respond to women who have experienced trauma in everyday hostel work; including training for workers, psycho-education groups and symptom management | GPH | DLUHC funding allocated in 2021-22 provision to work with women with no recourse to public funds, this service will also support women with dogs who traditionally refuse accommodation if the pet is not allowed into accommodation and those who have chaotic substance use and behaviour challenges. The service will continue to be inclusive for transgender women. WCC respite room accommodation working with St Mungo’s in partnership with WCC. 13 on-suite bedrooms within 4 dedicated clusters with kitchen facilities within a female only 24/7 staff building. The service will continue to accept women who regularly face barriers to accessing services. Expansion of the Solace Housing First meeting the needs of the most multiply disadvantaged female long term rough sleepers experiencing VAWG. Coordination will be provided by the post at Standing Together with a model to deliver Housing First principles. During 2021/22 the service enabled higher quality accommodation and support services. |  |  | As section 19 | GPH
22 |  | Match funding will be provided to continue the female entrenched rough sleeper project targeting older women with mental health problems moving across London boroughs up to 31 March 2018 | GPH | Build our understanding of the links between modern slavery and rough sleeping. We will continue to embed the Navigator Project and Multi-Agency Case Conferences across services in Westminster, as well as supporting a 6-month pilot expanding the Navigator project in LB Camden, led by The Passage. Additionally, we will support the Passage for funding to roll out the project across London. |  |  | Westminster will continue during 23-24 to commission services that lead on this Navigator project; building on the track record in the area of work to test out new approaches to supporting those who present to services as victims of modern slavery. WCC support the protocol sat alongside a council-wide referral pathway for victims of modern slavery. A wide range of joint working and essential services delivered through providers who continue to embrace solutions to the challenges in the areas of complex vulnerable people, traumatised by their experiences and how effective the collaboration of charities and other agencies, led by Westminster, can be through working together to break the cycle of homelessness for people with complex needs and to make a lasting difference to their lives. Playing a crucial role in supporting those most vulnerable people the new Modern Slavery Toolkit which will enable support those who are victims of modern slavery. | GPH

## PRIORITY C
Action Plan 2017-2022 |  |  |  |  | Action Plan 2023 - 24
Priority C: Protecting communities from ASB associated with rough sleeping and intervening to stop dangerous behaviour |  |  |  |  | Priority C: Protecting communities from ASB associated with rough sleeping and intervening to stop dangerous behaviour
Our Objectives | Our New Commitments | Responsibility of | Progress at 31 December 2022 | Comments | Our Objectives | Our New Commitments | Responsibility of | Update at 2023/24 | Comments
Rough Sleepers who refuse to engage and pose a danger to themselves or others are subject to enforcement action with a view to changing their behaviour | Jointly with the MET Police, we will develop a dedicated action plan to tackle street based ASB and criminality | GPH | During 2021/22 the Police established a Strategic Community Safety Board to provide strategic governance, leadership, drive and implementation of effective operational interventions to remove or reduce the impact of entrenched medium to long term crime and ASB issues impacting on communities. The group is chaired by the Central West BCU Superintendent head of Neighbourhoods Policing, with the Council’s Head of City-Wide Operations as vice chair. Meetings held every two months with a focus on existing and emerging problems and gaps with the ambition of proactively addressing challenges rather than reacting to them. |  |  | WCC will continue to support the Westminster Homelessness Partnership (WHP). Strategic delivery across agencies and multi-agency groups. | Growth Planning & Housing (GPH)
| We will provide all appropriate frontline staff (including partners staff) with information to share with rough sleepers on the support that is available to them and the consequences of not engaging or behaving anti-socially | CMC | Stakeholders identifying, in advance of the meeting, strategic crime and ASB problems to bring to the group. The focus of these meetings will be a collaborative workshop approach focused on highlighting the nature and extent of issues and agreeing action plans and responsible stakeholders. Issues will need to be based on evidence and analysis, however the meeting itself will avoid focusing overly on crime statistics, reports, and presentations as these are best suited to higher level strategic boards. Scoping and tasking the resources and assets available from statutory partners, third sector partners, and within communities to address problems. Linking to the operational work of the council chaired Neighbourhood Coordination Meetings (NCM) and the police Tactical Tasking and Co-ordination Group (TTCG). Ensuring links and coherence with other local governance such as the SYV Reduction Board, Youth Crime Partnership, Prevent Board, Adult and Children’s safeguarding arrangements and Violence Against Women and Girls (VAWG). Placing residents’ needs and views at the centre of problem-solving responses and, where appropriate, to develop problem-solving solutions with them. Defining mid-term strategic outcomes and work programmes and assuring delivery. Developing effective communication campaigns to promote local work in this area, and crime prevention messages. |  |  | WCC will continue to support the Westminster Homelessness Partnership (WHP). Strategic delivery across agencies and mutli-agency groups | GPH
| Where necessary and appropriate, we will look to work with organisations and services to provide security which will address issues inside the facilities used by rough sleepers and in the surrounding area. | CMC | The group reported annually to the Safer Westminster Partnership with a core membership that included, Superintendent - Central West Neighbourhoods Policing (Chair), Chief Inspector - Central West Neighbourhoods Policing, Chief Inspector - Central West Neighbourhoods Partnership and Prevention, DCI - Central West CID – CDI Gail Granville, Director of Family Services WCC, Head of Early Help and Youth Offending WCC, Head of Service MASH, IGXU, Access & Assessment, Head of Safeguarding Review and Quality Assurance, WCC, Executive Director of Environment and City Management, Director of Westminster Housing, Director of Public Protection and Licensing WCC, Cabinet Member for Communities and Regeneration, Westminster IAG Chair, Chair of Safer Business Network |  |  | WCC will continue to support the BIDS and the wider work to developing stakeholder relationships and opportunities during 23-24. | GPH
| We will work towards embedding the use of rough sleeping assessments and data in our City Management services to ensure that enforcement is only undertaken in full knowledge of an individuals situation and only as a last resort. This will allow us to target our enforcement efforts on those individuals who may benefit the most from our intervention whilst ensuring that we are protecting communities from their behaviour | CMC | As above |  |  | As above | GPH
| We will maximise the impact of our on-street presence through our frontline staff, from our City Inspectors to our parking marshals and waste contractors, getting them to act as the eyes and ears of the council in implementing this approach to enforcement. | CMC | As above |  |  | As above | GPH